## Sheet1
| time | week 1 |  | week 2 |  | week 3 | week 4 |  | week 5 | week 6 |  |  | Week 7 |  | Week 8 | Week 9 | Week 10 |  | Week 11 |  | Week 12 | Week 13 | Week 14 |  | Week 15 |  | Week 16 |  | Week 17 | Week 18 |  | Week 19 | Week 20 |  | Week 21 |  | Week 22 |  | Week 23 | Week 24 |  | Week 25 | Week 26
tasks |  | October |  |  |  | November | [5 empty] | December | [5 empty] | January | [5 empty] | Febuary | [6 empty] | March | [6 empty] | April
PLAN |  | Plan
PLAN |  | Overview
PLAN |  |  | WBT
PLAN |  |  | Converse Ideas
PLAN |  |  | Choose cloud
PLAN |  |  | Choose language
PLAN |  |  |  | PERT
PLAN |  |  |  | GANTT
PLAN |  |  |  |  | Report
ANALYSIS | [5 empty] | Analysis
ANALYSIS | [5 empty] | Functional
ANALYSIS | [5 empty] | non-functional
ANALYSIS | [5 empty] | technical
ANALYSIS | [6 empty] | inputs
ANALYSIS | [6 empty] | outputs
ANALYSIS | [7 empty] | printouts
ANALYSIS | [8 empty] | potential problems
DESIGN | [9 empty] | Design
DESIGN | [9 empty] | General Templates
DESIGN | [10 empty] | Survey
DESIGN | [11 empty] | Note (in)consistencies
DESIGN | [11 empty] | Draft forms
DESIGN | [14 empty] | Technical drawings
DESIGN | [15 empty] | Create output templates
DESIGN | [15 empty] | Create input templates
DESIGN | [17 empty] | Print-out templates
DESIGN | [9 empty] | Class Diagrams
DESIGN | [10 empty] | Pseudocode
DESIGN | [10 empty] | Algorithms
DESIGN | [13 empty] | Proof
DESIGN | [13 empty] | Complexity
DESIGN | [13 empty] | Test Plan
DESIGN | [19 empty] | Storyboard
CODE | [21 empty] | Code
CODE | [21 empty] | Draw UML/Technical Diagrams
CODE | [23 empty] | Split Tasks (Code)
CODE | [23 empty] | Debug
CODE | [25 empty] | Create GUI
CODE | [27 empty] | Modular Testing
CODE | [33 empty] | remove debug code
TESTING | [35 empty] | Testing
TESTING | [35 empty] | Documentation
TESTING | [35 empty] | Input validation
TESTING | [37 empty] | Output testing
TESTING | [39 empty] | Integration/Crash
TESTING | [39 empty] | Functional
TESTING | [40 empty] | Platform
TESTING | [41 empty] | Integration
INTEGRATION | [41 empty] | publish
INTEGRATION | [41 empty] | User Manual
INTEGRATION | [41 empty] | readme
INTEGRATION